## Sheet1
Construction management Plan | obtained and on site
Encroachment/Obstruction | obtained and on site
traffic plan required/approved
Survey/elevation | Preconstruction meeting
survey required
building corners staked
blue top stake
property staked
elevation of upstream manhloe cover
Grading | Preconstruction meeting
Portable toilets shall have secondary containment and be placed 50ft from drain inlet
BMP's for particular site
drainge flow in street and lot established
amount of cut/fill/truck tags/ and planned location of cut material
creek protection | Permit required/obtained. Measures to protect creek and riparian zone in place
tree protection | tree root zone protection/tree permit for protected trees
Clearing and Grubbing | Plan for clearing and grubbing and replanting
erosion and dust control | SWPPP plans onsite including storm drain protection and construction entrance
wattles in place
Dirt stockpiles covered and weighed with sand bags
silt fencing where required.
jute netting or hydroseeding required
preservation of existing vegetation
geotextiles and mats
earth dikes and drainage swales
sreatmbank stabilization
velocity dissapation
wood muclhing
soil binders
wattles in place
C6 and rainwater runoff | SWPPP plans onsite
stabilized construction entrance
stabilized constgruction road
DI protection
street sweeper sweeping and vaccuming
Entrance/outlet tire washout area
wattles in place
stockpiles covered and weighed with sand bags
silt fencing where required.
jute netting or hydroseeding required
wattles in place
straw bale barrier
sand bag barrier
gravel bag berm
check dams
Riprap in place at construction entrance
ratttle plate
tire washing station
street sweeper
Material storage/containment
bio filter bags
temp. silt dike
sediment basin
Active treatment system
Compost socks and berms
Temporary silt dike
non storm erosion controls
excavation/shoring | Shoring and grading plan on site
Cut and fill demarcation determined an quantities match engineers estimate
soils report with grading plan
amount of pervious and impervious proposed area
drainage from excavation accounted for in BMPS
protected trees from root zone to drip line
Location of utilities
Pipe materials, gradients and sizes
Creek protection permit and riparian zone required
Traffic control/parking | required obstruction permits obtained
Traffic plan and truck route approved by TSD
Flag person stationed for lane closures
Blight/noise toilet | Portable toilets have secondary containment
Portable toilets not in ROW and place as far from DI as possible
Excessive noise does not exceed what is approved in CMP
working hrs in CMP are being adhered to
Site is kept clean of debris, mud and does not create a blighted site
INFRASTRUCTURE | sewer materaials approved and correctly bedded
Plasitic sewers bedding and trinching shall conform to ASTM 2321
Required backwater vavles are installed only on floors containing fixtures below the next upstream man hole cover
Sewer overflow devices installed at building sewer cleanout
stormdrains | Storm drain piping is approved material/pump stations must be approved with energy dissapation
Storm drain cuts at curb shall be constructed to City detail
All sormwater connections shall discharge to appoved location (street)or retained on site (pervious surface)
Required C3 measures for new construction per approved plans
Drainage | Grade shall slope away from building 2%for first 10 ft
Detached retaining walls shall be provided with drainage and weep holes
compaction requried before final
BMP's in place
Hardcape | Hardscape/impervious surface shall not form concentrated flow across neighbors property
C3 treatment measures for new construction that adds 2500 sq ft of new impervious surface
shared driveway | Driveway in approved location (per plan) and sloped according to plan and City
C3 facility | C3 treatment measures for new construction that adds 2500 sq ft of new impervious surface
C3 treatment measures are per approved plans. (NO ALTERNATIVES ALLOWED WITHOUT REVISION)
Grading | clearing and grubbing/suitable subgrade or bedrock exposed but no fill material
elevation of garage pad (up and down slopes) first floor at level lots . Provide Blue Top stake
Elevation of upstream manhole cover established
Corners staked at property and building corners
driveway slopes established to plans
Toe and key for slope fills
After excavation but prior to filter and subdrain, pipe and filter material shall be on site for inspection
Inspection required after drain and filter material placed but prior to fill
Excavation and fills | Inspection to verify pad elevations including SI report from designer
Verify grade will slope away from building 2% for first 10ft
inspection after excavation but before reaching a depth of 10 ft or fill reaching 10ft
PAD | Inspection of prepared Subgrade for driveway (on Private property) to be in place for rough grading approval
Subgrade inspection and forms in place prior to placemant of structures.
Provide special inspection that line grade is within .02 percent of the approved plans
Sub Grade | Check that all grading is complete and compacted
Concrete and gunite structures | Sidewalk and driveway apron bedding and compaction report/through curb drains /energy dissapators in place
Final | All forms to be in place according to approved plans and 2% min cross slope on sidewalk acheived
Sidewalk and Driveway Apron | FINAL ROW
Private Sewer Lateral | PSL certificate obtained before ROW finaled
Fire sprinkler | Fire sprinkler rough
Fire Final | Fire Marshal final
Landscape/Hardscape | Inspect for compliance with conditions of approval for landscaping/hardscape
Site improvements | All conditions of approval for site work is completed per Zoning COA
Final | All Zoning conditions have been met including design review, building height, and Misc COA